## PROJECT
PROJECT
PROJECT NAME | OrangeHRM | Browser Tested | Chrome & Firefox
Project URL | https://opensource-demo.orangehrmlive.com | CROSS BROWSER TESTED | Yes
Assigned By | Self | Build Version | 1.0
Assigned Date | 2025-05-18 | Tools Used | Excel, Postman, Jira(demo)
Sprint | Sprint 1 | Description | Manual testing on login, leave, admin & time

## PROJECT DETAILS
PROJECT DETAILS (OrangeHRM Demo)
Module Name | Assigned Date | Assigned By | Sprint | Browser Version | Build No. | Cross-Browser Testing | Status
Login | 2025-05-18 | Self | Sprint 1 | Version 136.0.7103.114 | 1.0 | Yes | Complete
Admin - Add User | 2025-05-18 | Self | Sprint 1 | Version 136.0.7103.114 | 1.1 | Yes | Complete
PIM | 2025-05-18 | Self | Sprint 1 | Version 136.0.7103.114 | 1.2 | Yes | Complete
Leave | 2025-05-18 | Self | Sprint 1 | Version 136.0.7103.114 | 1.3 | Yes | Complete
Time | 2025-05-18 | Self | Sprint 1 | Version 136.0.7103.114 | 1.4 | Yes | Complete
Directory | 2025-05-18 | Self | Sprint 1 | Version 136.0.7103.114 | 1.5 | Yes | Complete
Performance | 2025-05-18 | Self | Sprint 1 | Version 136.0.7103.114 | 1.6 | Yes | Complete
Dashboard | 2025-05-18 | Self | Sprint 1 | Version 136.0.7103.114 | 1.7 | Yes | Complete

## DECISION TABLE
DECISION TABLE
ATTRIBUTES | TC001 | TC002 | TC003 | TC004 | TC005 | TC006 | TC007 | TC008 | TC009 | TC010
Username | Valid | Valid | Invalid | Valid | Blank | Blank | Invalid | Invalid | Blank | Blank
Password | Valid | Invalid | Valid | Blank | Valid | Invalid | Blank | Invalid | Blank | Valid
Login Button Clicked | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No
Actual Result | Success | Error | Error | Error | Error | Error | Error | Error | Error | Error
Expected Result | Success | Error | Error | Error | Error | Error | Error | Error | Error | Error

## TEST SCENARIO
TEST SCENARIOS
SR NO. | TEST SCENARIO ID | Module | TEST SCENARIO | TOTAL NO. OF CASES
1 | SC-001 | Login | Login with Valid Credentials | 1
| SC-002 |  | Login with Invalid Credentials/Blanks | 8
| SC-003 |  | Password field is masked | 1
2 | SC-004 | Admin | Add a new user with valid data | 1
| SC-005 |  | Try adding a new user with existing username | 1
| SC-006 |  | Submit form with missing required fields | 1
| SC-007 |  | Cancel button on form | 1
3 | SC-008 | Leave | Apply for leave with valid dates and types | 1
| SC-009 |  | Try applying for leave without selecting date or type | 1
| SC-010 |  | Cancel a leave request | 1
| SC-011 |  | View leave list by filter | 1
4 | SC-012 | PIM | Add employee with complete info | 1
| SC-013 |  | Edit employee information | 1
| SC-014 |  | Search employee by name | 1
5 | SC-015 | Time | Submit Timesheet | 1
| SC-016 |  | Edit existing timesheet | 1
6 | SC-017 | Directory | Search employees in directory | 1
| SC-018 |  | Search with empty inputs | 1
7 | SC-019 | Dashboard | View Dashboard elements(pending leave,birthdays) | 1

## TEST CASES
TEST CASES
TC ID | TEST SCENARIO | TEST CASE DESCRIPTION | TEST CASE TYPE | PRE-CONDITIONS | TEST STEPS | TEST DATA | EXPECTED RESULT | POST CONDITION | ACTUAL RESULT | STATUS
OH-01 | Logiin | Validate login functionality with valid credentials | Positive | Valid Username & Password | 1) Open Browser | admin | Login should succeed | Should land on the Dashboard | SUCCESS | PASS
[5 empty] | 2) Enter Valid Username | admi123
3)Enter Valid Password
4) Click the Button
OH-02 | Login | Validate Login with Valid username and invalid password | Negative | Valid Username & Invalid Password | 1) Enter Valid Username | admin | Error should pop-up | Should stay on the login page | SUCCESS | PASS
[5 empty] | 2)Enter InValid Password | xzxzxx
3) Click the Button
OH-O3 | Login | Validate Login with Invalid Username and Valid password | Negative | Invalid Username and Valid password | 1) Enter Invalid Username | xzxzxx | Error should pop-up | Should stay on the login page | SUCCESS | PASS
[5 empty] | 2)Enter Valid Password | admin123
3) Click the Button
OH-04 | Login | Validate Login with valid Username and blank password | Negative | Valid Username and blank password | 1) Enter Valid Username | admin | Error should pop-up | Should stay on the login page | SUCCESS | PASS
[5 empty] | 2)Leave Password blank | Blank
3) Click the Button
OH-05 | Login | Validate Login with Blank Username and valid password | Negative | Login with Blank Username and valid password | 1) Leave Username Blank | Blank | Error should pop-up | Should stay on the login page | SUCCESS | PASS
[5 empty] | 2)Enter Valid Password | admin123
3) Click the Button
OH-06 | Login | Validate Login with Blank Username and invalid password | Negative | Blank Username and invalid password | 1) Leave Username Blank | Blank | Error should pop-up | Should stay on the login page | SUCCESS | PASS
[5 empty] | 2)Enter Invalid Password | xzxzxx
3) Click the Button
OH-07 | Login | Validate Login with Invalid Username and blank password | Negative | Invalid Username and blank password | 1) Enter Invalid Username | xzxzxx | Error should pop-up | Should stay on the login page | SUCCESS | PASS
[5 empty] | 2)Leave Password blank | Blank
3) Click the Button
OH-08 | Login | Validate Login with Invalid Username and password both | Negative | Invalid Username and invalid password | 1) Enter Invalid Username | xzxzxx | Error should pop-up | Should stay on the login page | SUCCESS | PASS
[5 empty] | 2)Enter Invalid Password | xzxzxx
3) Click the Button
OH-09 | Login | Validate Login with Both Username and password blank | Negative | Login with Both Username and password blank | 1) Leave Username Blank | Blank | Error should pop-up | Should stay on the login page | SUCCESS | PASS
[5 empty] | 2)Leave Password blank | blank
3) Click the Button
OH-10 | Login | Validate the password masks input with astericks or dots | UI/UX validation | Password field is masked | 1) Leave Username Blank | Blank | Password should appear as ●●●●●● | Should stay on the login page | SUCCESS | PASS
|  | Typed characters are not visible |  |  | 2)Enter any Password | xzxzxx
3) Click the Button
OH-11 | Admin | Add a new user with valid data | Positive | User is logged in as an Admin and on add user | 1) Click on the Admin | Admin/Ess | User is added successfully and appears in the list | New user is created | SUCCESS | PASS
[5 empty] | 1) Fill the form with valid data | Username: Ali
3) Click the Search
OH-12 | Admin | Try adding a new user with existing username | Negative | A user with the same data already exists | 1) Fill the form with an existing username | xzxzxx | Error should pop-up | No user is created | SUCCESS | PASS
2) Click save
OH-13 | Admin | Submit form with missing required fields | Negative | Admin is on add user page | 1) Leave all fields blank
[5 empty] | 2) Click save | Blank | Error should pop-up | No user is created | SUCCESS | PASS
OH-14 | Admin | Cancel button on form | Positive | Admin is on partially-filled add user form | 1) Start filling | Valid/Invalid dara | Form is reset or redirected to user list | No user is created, field cleared | SUCCESS | PASS
2) Click save
OH-15 | Leave | Apply for leave with valid dates and types | Positive | User logged in, on apply leave page | 1) Select leave | 2025-01-05 | Leave request submitted successfully | Leave request listed | SUCCESS | PASS
2) Pick valid date range
3) Add comment
4)Click apply
OH-16 |  | Try applying for leave without selecting date or type | Negative | User on Apply, Leave page | 1) Choose Leave type | Blank | Error should pop-up | No leave request is created | SUCCESS | PASS
2) Leave date blank
3) Click apply
OH-17 |  | Cancel a leave request | Positive | Leave already applied | 1) Click leave list |  | Leave status changes to cancelled | Leave removed from active list | SUCCESS | PASS
2) Cancel leave request
OH-18 |  | View leave list by filter | Positive | User on leave list page | 1) Select valid date range + status | 2025-01-05 | Filtered leave entries appear | UI filter applied | SUCCESS | PASS
2) Click search
OH-19 | PIM | Add employee with complete info | Positive | Add valid data of employee | 1)User on PIM | Ali | Employee added and listed | New employee created | SUCCESS | PASS
2) Add employee
OH-020 |  | Edit employee information | Positive | Employee already exists | 1) Search
2) Click edit
3) Update fields
4) Click save
OH-021 |  | Search employee by name | Positive | At least 1 employee exists | 1)Type name | Ali | Matching results displayed | Changes reflected in profile | SUCCESS | PASS
2) Click search
OH-022 | Time | Submit Timesheet | Positive | User on Timesheet page | 1) Select week | 4th | Timesheet submitted successfully | Status: Submitted | SUCCESS | PASS
2) Click submit
OH-023 |  | Edit existing timesheet | Positive | Timesheet already exists | 1) Click edit | 12 | Timesheet updated | Changes reflected | SUCCESS | PASS
2) Update hours
3) Click save
OH-024 | Directory | Search employees in directory | Positive | Directory has users | 1) Type employee name | Ali | Matching employees appear | View-only | SUCCESS | PASS
2) Click search
OH-025 |  | Search with empty inputs | Negative | User on Directory page | 1) Leave search field blank | Blank | Error should pop-up | No change | SUCCESS | PASS
2) Click search
OH-026 | Dashboard | View Dashboard elements(pending leave,birthdays) | Positive | User logged in | 1)Login | admin | Widgets should appear | Read-only dashboard | SUCCESS | PASS
[5 empty] | 2) Land on Dashboard | admin123

## API TESTING
API TESTING
API Test ID | MODULE NAME | ENDPOINT | METHOD | REQUEST PAYLOAD | RESPONSE | TOOLS USED
API001 | Login | /auth/login | Post | {username, password} | Authenticate user | Postman
API002 | Employee | /employee/add | Get | {name, role, status} | Employee added | Postman
API003 | Leave | /leave/apply | Post | {leaveType date} | {Leave request created} | Postman
API004 | Leave | /leave/list | Get | - | Leave entries returned | Postman
API005 | Directory | /directory/search | Get | ?name=xyz | Employee results shown | Postman

## BUG REPORT
Note: These are simulated bugs used for practice and presentation. Actual testing did not reveal functional issues in the OrangeHRM demo site.
BUG REPORT
BUG ID | MODULE | Tittle | Steps to Reproduce | EXPECTED RESULT | ACTUAL RESULT | SEVERITY | PRIORITY | STATUS | SCREENSHOT
BUG001 | Login | No error when both fields are blank | 1) Leave username and password blank | Error message shown | No error appears | High | Urgent | Open
2) Click login
BUG002 | Admin | Paasword not masked in add user | 1) Go to add user | Should be masked | Text is visible | Medium | High | Open
2) Type password
BUG003 | Leave | Can apply leave without selecting date | 1)Select type only | Error: Date required | Leave request submited | Low | Low | Open
2) Click apply
BUG004 | Directory | Search doesn't return accurate results | 1) Enter existing employee name | Matching employee shown | No record found | Medium | High | Open
2) Click search
BUG005 | PIM | Can save blank employee | 1) Leave name fields blank | Validation errors shown | Form Submitted | High | High | Open
2) Click save

## TEST SUMMARY SHEET
TEST SUMMARY
TOTAL TEST CASES | PASSED | FAILED | BLOCKED | BUGS LOGGED | MODULES COVERED | TOOLS USED
26 | 26 | 0 | 0 | 5 | Login, Admin, Leave, PIM, Time, Directory, Dashboard | Postman, Chrome, Firefox, Jira(Manual)